## Sheet1
ID | WBS (work Breakdown Structure) | Predecessor | Duration | RESOURCE
1 | Poster competition
2 | 1 Initiating
3 | 1.1 Project manager selecting (main organizer of the project) |  | 1d | HOD
4 | 1.2 Developing project charter | 3 | 7d | HOD, X
5 | 1.3 Approving project charter | 4 | 1d | HOD | HR
6 | 1.4 First meeting | 8 | 4h |  | MACHINE
7 | 2 Planning |  |  |  | MATERIAL
8 | 2.1 Selecting faculties | 5 | 2h
9 | 2.2 Selecting volunteers | 6 | 2d
10 | 2.3 Developing schedule | 6 | 3d
11 | 2.4 Listing resource requirements | 6, 17 | 2d
12 | 2.5 Developing budget | 11, 13, 18 | 3d | COMP, X
13 | 2.6 Selecting venue | 10 | 1d
14 | 2.7 Selecting judge | 6 | 2d
15 | 2.8 Selecting participants | 6 | 2d
16 | 2.9 Selecting guests | 6 | 2h
17 | 2.10 Generating decorating ideas | 9 | 3d
18 | 2.11 Selecting refreshments | 11 | 2d
19 | 2.12 Selecting poster collection venue | 10 | 1d
20 | 2.13 Designing banner | 10, 12 | 3d | BANNER 3, VOLUNTEER 2
21 | 3 Executing
22 | 3.1 Collecting posters | 15,19 | 4h
23 | 3.2 Sorting posters for display | 22 | 1d
24 | 3.3 Buying decorating items | 17 | 2d
25 | 3.4 Announcing the event | 10 | 7d
26 | 3.5 Handling event day
27 | 3.5.1 Decorating display area
28 | 3.5.1.1 Arranging flowers | 24 | 2h
29 | 3.5.1.2 Collecting banner | 20 | 2h
30 | 3.5.1.3 Hanging banner | 29 | 1h
31 | 3.5.1.4 Arranging paper crafts | 24 | 1h
32 | 3.5.1.5 Arranging balloons | 24 | 2h
33 | 3.5.2 Cleaning display area | 25 | 2h
34 | 3.5.3 Displaying posters | 16,23, 27 | 2h
35 | 3.5.4 Judging posters | 14, 34 | 2h
36 | 3.5.5 Selecting winners | 35 | 2h
37 | 3.5.6 Providing refreshments to judges | 35, 18 | 30m
38 | 4 Monitoring and Controling
39 | 4.1 Meeting weekly | 8 | 2h | recurring
40 | 4.2 Emailing updates | 8 | 1h | recurring
41 | 5 Closing
42 | 5.1 Closing speech by the HOD | 37 | 10min
43 | 5.2 Awarding certificates to winners | 42 | 2h
44 | 5.3 Clearing display area | 43 | 2h

## Sheet2
WBS Work break down structure
ID | Work Package | Predecessor | Duration
1 | Poster competition
2 | 1 Initiating
3 | 1.1 Project manager selecting (main organizer of the project) |  | 1d
4 | 1.2 Developing project charter | 3 | 7d
5 | 1.3 Approving project charter | 4 | 1d
6 | 1.4 First meeting | 8 | 4h
7 | 2 Planning
8 | 2.1 Selecting faculties | 5 | 2h
9 | 2.2 Selecting volunteers | 6 | 2d
10 | 2.3 Developing schedule | 6 | 3d
11 | 2.4 Listing resource requirements | 6, 17 | 2d
12 | 2.5 Developing budget | 11, 13, 18 | 3d
13 | 2.6 Selecting venue | 10 | 1d
14 | 2.7 Selecting judge | 6 | 2d
15 | 2.8 Selecting participants | 6 | 2d
16 | 2.9 Selecting guests | 6 | 2h
17 | 2.10 Generating decorating ideas | 9 | 3d
18 | 2.11 Selecting refreshments | 11 | 2d
19 | 2.12 Selecting poster collection venue | 10 | 1d
20 | 2.13 Designing banner | 10, 12 | 3d
21 | 3 Executing
22 | 3.1 Collecting posters | 15,19 | 4h
23 | 3.2 Sorting posters for display | 22 | 1d
24 | 3.3 Buying decorating items | 17 | 2d
25 | 3.4 Announcing the event | 10 | 7d
26 | 3.5 Handling event day
27 | 3.5.1 Decorating display area
28 | 3.5.1.1 Arranging flowers | 24 | 2h
29 | 3.5.1.2 Collecting banner | 20 | 2h
30 | 3.5.1.3 Hanging banner | 29 | 1h
31 | 3.5.1.4 Arranging paper crafts | 24 | 1h
32 | 3.5.1.5 Arranging balloons | 24 | 2h
33 | 3.5.2 Cleaning display area | 25 | 2h
34 | 3.5.3 Displaying posters | 16,23, 27 | 2h
35 | 3.5.4 Judging posters | 14, 34 | 2h
36 | 3.5.5 Selecting winners | 35 | 2h
37 | 3.5.6 Providing refreshments to judges | 35, 18 | 30m
38 | 4 Monitoring and Controling
39 | 4.1 Meeting weekly | 8 | 2h
40 | 4.2 Emailing updates | 8 | 1h
41 | 5 Closing
42 | 5.1 Closing speech by the HOD | 37 | 10min
43 | 5.2 Awarding certificates to winners | 42 | 2h
44 | 5.3 Clearing display area | 43 | 2h