## Slide 1: Introduction to CPM

## Slide 2: Project Management

Managers have been planning, scheduling, monitoring, and controlling large scale projects for hundred years, but it has only been in the last 50 years that management science techniques have been applied to major projects.

They are two types:
Critical Path Method(CPM)
Project Evaluation and Review Technique(PERT)

## Slide 3:  Critical path is the sequential activities from start to the end of a project. Although many projects have only one critical path, some projects may have more than one critical paths depending on the flow logic used in the project
 The essential technique for using CPM is to construct a model of the project that includes the following:


A list of all activities required to complete the project (typically categorized within a work breakdown structure
The time (duration) that each activity will take to completion,
The dependencies between the activities

.

## Slide 4: Terminologies used in CPM
In order to explain the purpose, structure and operation of CPM, it is helpful to define the following terms:
Activity: An activity carries the arrow symbol.This represent a task or subproject that uses time or resources
Event:- A node (an event), denoted by a circle
, marks the start and
completion of an activity, which contain a number that helps to identify its location. For example activity A can be drawn as:
Dummy Activity: An activity, which is used to maintain the pre-defined precedence relationship only during the construction of the project network, is called a dummy activity. Dummy activity is represented by a dotted arrow and does not consume any time and resource
2
1
A

## Slide 5
 Parallel activity: There are two activity which being at same event and end at same event.this activities are called parallel activity.
Not allowed…..
 Path: A path is a series of adjacent activities leading from one event to another.
 Critical path: A critical path is the sequence of critical activities that forms a continuous path between the start of a project and its completion.

## Slide 6: Situations in network diagram B
A
A must finish before either B or C
can start, it called burst event.
C
A
B
C
both A and B must finish before C
can start, it called merge event.
Dangling events is not allow.
A
C
B
D
Dummy
A must finish before B can start
both A and C must finish before D can start, it’s called dummy activity.
A
B
C

## Slide 7: Forward pass:
 The Early Start and Early Finish Time Calculated by moving Forward Through the Network.
 More than one predecessor Consider Maximum.
ES/EST
EF/EFT
Backward pass:
 The Latest Start and Latest Finish Time Calculated by moving Backward Through the Network.
 More than one follower Consider Minimum
LS
LF

## Slide 8: Float activity:
 Float activity For an Activity is The Difference between its Earliest and Latest Start Time or Earliest and Latest Finish Time .
Float/Slack= (LS – ES)
Or ( LF – EF)
EF = ES + t
LS = LF - t
Forward pass
Backward pass

## Slide 9: Steps in Critical Path Method
 Step 1: Make a forward pass through the network as follows: For each activity i beginning at the Start node, compute:
Earliest Start Time (ES) = the maximum of the earliest finish times
of all activities immediately preceding activity i. (This is 0 for an activity with no predecessors.). This is the earliest time an activity can begin without violation of immediate predecessor requirements.
Earliest Finish Time (EF) = (Earliest Start Time) + (Time to complete activity i. This represent the earliest time at which an activity can end.
The project completion time is the maximum of the Earliest Finish Times at the Finish node.
EF = ES + t

## Slide 10: Continue..........
 Step 2: Make a backwards pass through the network as follows: Move sequentially backwards from the Finish node to the Start node. At a given node, j, consider all activities ending at node j. For each of these activities, (i,j), compute:
Latest Finish Time (LF) = the minimum of the latest start times beginning at node j. (For node N, this is the project
completion time.). This is the latest time an activity can end without delaying the entire project.
Latest Start Time (LS) = (Latest Finish Time) - (Time to complete activity (i,j)). This is the latest time an activity can begin without delaying the entire project.
LS = LF - t

## Slide 11
SSS
A
B
C
D
E
F
G
AOA network diagram
S
Activity
Time
LS | Slack | LF
ES | t | EF
Each activity, EF=ES+t
At starting activity, ES=0
Follower ES= Predecessor EF
Forward pass
Each activity, LS=LF - t
At ending activity, LF=EF
Predecessor LF=Follower LS
Backward pass
Slack=LS-ES
Or LF-EF
Critical path=A-E-G=20 weeks
Project completion time =20 weeks
Activity ID | Predecessor | Duration in weeks
A | - | 8
B | - | 4
C | B | 9
D | A | 6
E | A | 11
F | D | 3
G | C, E, F | 1
10 | 2 | 16
8 | 6 | 14
19 | 0 | 20
19 | 1 | 20
8 | 0 | 19
8 | 11 | 19
16 | 2 | 19
14 | 3 | 17
10 | 6 | 19
4 | 9 | 13
6 | 6 | 10
0 | 4 | 4
0 | 0 | 8
0 | 8 | 8

## Slide 12
Activity ID | Predecessor | Duration in weeks
A | - | 8
B | - | 4
C | B | 9
D | A | 6
E | A | 11
F | D | 3
G | C, E, F | 1
AON Diagram
S
A
B
C
D
E
F
G
LS | Slack | LF
ES | t | EF
8 | 0 | 19
8 | 11 | 19
10 | 6 | 19
4 | 9 | 13
19 | 0 | 20
19 | 1 | 20
16 | 2 | 19
14 | 3 | 17
10 | 2 | 16
8 | 6 | 14
6 | 6 | 10
0 | 4 | 4
Critical Path = S-A-E-G = 20 weeks
0 | 0 | 8
0 | 8 | 8

## Slide 13: Continue..........
 Step 3: Calculate the float time for each activity by:
float = (Latest Start) - (Earliest Start), or
= (Latest Finish)-(EarliesFinish).
A critical path is a path of activities, from the Start node to the Finish node, with 0 float times.

## Slide 14: Example
1. Construct the CPM Network (AOA and AON using the details below and determine the critical path using CPM.
Activity
Immediate predecessors
-
A A
C
D
B, E
F
Completion Time (week)
2
3
3
4
8
6
A B C D E F G
2

## Slide 15
Activity
Immediate predecessors
-
A A
C
D
B, E
F
Completion Time (week)
2
3
3
4
8
6
A B C D E F G
2
A
B
C
D
E
F
G
LS | Slack | LF
ES | t | EF
0 | 0 | 2
0 | 2 | 2
17 | 0 | 23
17 | 6 | 23
9 | 0 | 17
9 | 8 | 17
5 | 0 | 9
5 | 4 | 9
2 | 0 | 5
2 | 3 | 5
14 | 12 | 17
2 | 3 | 5
23 | 0 | 25
23 | 2 | 25
Critical path= A-C-D-E-F-G

## Slide 16: Benefits of CPM
 Useful at many stages of project management
 Mathematically simple
 Give critical path and float time
 Provide project documentation
 Useful in monitoring costs
 Visual representation

## Slide 17
2. The following table contains information related to the major activities of a research project. Use the information to do the following: a. Draw a precedence diagram using AOA /AON. b. Find the critical path using CPM. c. Determine the expected length of the project.
Activity | Predecessor | Time in days
a | ---- | 5
c | a | 8
d | c | 2
b | a | 7
e | --- | 3
f | e | 6
i | b, d | 6
m | f, i | 8
g | --- | 1
h | g | 2
k | h | 17
end | k, m | 
a
e
g

## Slide 18
Activity | Predecessor | Time in days
a | ---- | 5
c | a | 8
d | c | 2
b | a | 7
e | --- | 3
f | e | 6
i | b, d | 10
m | f, i | 8
g | --- | 1
h | g | 2
k | h | 17
end | k, m | 
LS | Slack | LF
ES | t | EF
5 | 0 | 13
5 | 8 | 13
a
e
g
c
d
b
f
i
m
h
k
end
33 | 0 | 33
33 | 0 | 33
16 | 13 | 33
3 | 17 | 20
14 | 13 | 16
1 | 2 | 3
13 | 0 | 15
13 | 2 | 15
13 | 13 | 14
0 | 1 | 1
16 | 16 | 19
0 | 3 | 3
19 | 16 | 25
3 | 6 | 9
8 | 3 | 15
5 | 7 | 12
25 | 0 | 33
25 | 8 | 33
15 | 0 | 25
15 | 10 | 25
0 | 0 | 5
0 | 5 | 5

## Slide 19
S
a
e
g
c
d
b
f
i
m
h
k
end
AON diagram
LS | Slack | LF
ES | t | EF
16 | 16 | 19
0 | 3 | 3
8 | 3 | 15
5 | 7 | 12
15 | 0 | 25
15 | 10 | 25
5 | 0 | 13
5 | 8 | 13
13 | 0 | 15
13 | 2 | 15
0 | 0 | 5
0 | 5 | 5
13 | 13 | 14
0 | 1 | 1
19 | 16 | 25
3 | 6 | 9
25 | 0 | 33
25 | 8 | 33
16 | 13 | 33
3 | 17 | 20
14 | 13 | 16
1 | 2 | 3
33 | 0 | 33
33 | 0 | 33

## Slide 20
Activity | Predecessor | Time in days
A | - | 2
D | A | 6
E | D | 7
H | E | 2
F | A | 3
G | F | 5
B | — | 3
I | B | 6
J | I | 5
K | J | 8
C | — | 12
M | C | 1
N | M | 11
O | N | 13
End | H, G, K, O | 
The following table contains information related to the major activities of a research project. Use the information to do the following: a. Draw a precedence diagram using AOA and Gantt chart. b. Find the critical path using CPM. c. Determine the expected length of the project.
Assignment 4

## Slide 21
Activity | Predecessor | Time in days
A | - | 2
D | A | 6
E | D | 7
H | E | 2
F | A | 3
G | F | 5
B | — | 3
I | B | 6
J | I | 5
K | J | 8
C | — | 12
M | C | 1
N | M | 11
O | N | 13
End | H, G, K, O | 
AON Diagram
D
A
B
C
D
E
H
F
G
I
J
K
M
N
O
End
S

## Slide 22
ACITIVITY | Duration | Immediate Predecessor
A | 1 Day | n/a
B | 2 Days | n/a
C | 3 Days | n/a
D | 4 Days | A
E | 5 Days | B
F | 4 Days | B
G | 6 Days | C
H | 6 Days | D, E
I | 2 Days | G
J | 3 Days | H, F, I

## Slide 23
Sample Problem #1
Activity | Immediate Predecessor(s) | Duration (Weeks) |  | Activity | Immediate Predecessor(s) | Duration (Weeks)
N |  | 5 |  | G | B | 2
A | N | 4 |  | H | B | 16
B | N | 10 |  | I | H | 4
C | N | 7 |  | J | H | 8
D | A | 5 |  | K | I, J, L | 5
E | D, G | 3 |  | L | C | 9
F | E | 6 |  | M | J, L | 10

## Slide 24
Sample Problem #1
a) Draw the network diagram and find the critical path and project completion time.
b) Calculate float/ slack of the all activities.
c) Can activity I be delayed without delaying the project completion time? If so, how many weeks? How much dollar can be saved by keeping the project completion time unchanged, if $2500 can be saved for each delayed week of activity I?
d) What is the impact on the project if activity F needs a delayed time 2 weeks and extra time 5 weeks?
e) The PM wants to delay the duration of the activity M from 10 weeks to 16 weeks. What is the impact on the project completion time?

## Slide 25
Critical Path Analysis
Sample Problem # 2
Activity | Immediate Predecessor(s) | Duration (Weeks) |  | Activity | Immediate Predecessor(s) | Duration (Weeks)
A |  | 4 |  | F | B | 6
B |  | 10 |  | G | C | 2
C |  | 7 |  | H | F | 8
D | A | 5 |  | I | F, G | 11
E | B | 3 |  | J | D, E | 8

## Slide 26
Sample Problem # 2
Draw a network diagram and find the critical path and project completion time.
Calculate float/ slack of the all activities.
If $1000 can be saved for each delayed weeks of activity H, then how much dollar can be saved keeping the project completion time unchanged?
Activity G needs a delayed time of two weeks and an extra time of five weeks. Is it possible by keeping the project completion time unchanged? Explain.
The PM wants to shorten the duration of the activity I from 11 weeks to 9 weeks. What is the impact of this change on project completion time